| Area of Responsibility: Application of Problem Solving & Reasoning in Maths |  |  |  | Links with agencies: Maths SLE Assertive Mentoring (Assessment) Focus Education (Pre-teach Assessment) Lancs (Planning) |  |
| --- | --- | --- | --- | --- | --- |
| Objectives: 1) Progress towards 85% of children meeting year group expectations 2) Embedded opportunities to use and apply maths across the curriculum and throughout the school day 3) Opportunities to develop Problem Solving & Reasoning within maths 4) A consistent approach to planning and assessment in maths 5) Embedded opportunities to practise maths skills in ‘real-life’ contexts |  |  |  |  |  |
| 1) Progress towards 85% of children meeting year group expectations |  |  |  |  |  |
| Key Action | Leadership | Support | Resources | Success Criteria | Completion Date |
| 1a. Each year group (Y1-Y6) has a set of ‘non-negotiables’ and these are displayed in classrooms | Phase Leaders LT, JD, JB, CK | Maths leads, class teachers and support staff | Year-group generated non negotiables, printed and laminated | Year groups have a set of non-negotiables | September 2016 |
| 1b. Cycle of formative and summative assessments inform planning, enabling gaps to be plugged | Phase Leaders LT, JD, JB, CK | Class teachers, support staff, assessment team, SLT Mentors | Summative assessment materials | Formative and summative assessments used to plug gaps – increase in % of children meeting ‘expected’ throughout the year | Assessments to be carried out half termly |
| 1c. Rigour in planning enables the children to make maximum progress | Phase Leaders LT, JD, JB, CK | Class teachers and support staff Curriculum lead, SLT Mentors | Planning documents and resources | % of children making expected+ progress Planning shared and developed by teaching and support staff | Planning to be placed in shared area – by end of each week. (Reviewed half termly Phase Leaders) |
| 1d. Maths books are used to record learning in FS2 and reflect progress over time | EYFS Phase Leader LT | Class teachers, key workers | Maths books | Maths books reflect progress over time as evidenced through scrutiny | Reviewed half termly by EYFS phase leader |

Achieving Success Action Plan 2016-17

| 2. Embedded opportunities to use and apply maths across the curriculum and throughout the school day |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Action | Leadership | Support | Resources | Success Criteria | Completion Date |
| 2a) Maths continues to be taught weekly in subjects across the curriculum | Phase Leaders and Maths Team Jen D (EYFS) Hayley (KS1) Paul (KS2) | Class teachers and support staff, subject leads, SLT Mentors | Teaching and learning resources Phase Leadership time for book scrutiny and pupil voice | Termly book scrutiny shows consistent opportunities for using and applying skills in topic, termly pupil voice reflects opportunities available – including cookery and ICT | Reviewed termly within Phase Leader tasks set by SLT |
| 2b) Opportunities to develop mathematical skills are available in all areas of Continuous Provision in EYFS | Laura T | EYFS team Ellie Russell (T&L Governor) | Teaching and learning resources CP resources – to be purchased from EYFS cost centre | Opportunities for maths are identified by termly environment walks, evidence is included in all learning journeys and opportunities are discussed during governor T&L walks. | Reviewed termly by EYFS Phase Leader with learning walks |
| 2c) Opportunities for using and applying maths skills in the outdoor areas are used to enhance learning | Laura T, Jen D | EYFS team, Y1 team, class teachers and support staff | Teaching and learning resources Resources to be purchased from year group/class cost centres | Pupil voice reflects the opportunities available and impact is measured with regard to any benefits of such learning | Reviewed termly by KS1 & EYFS Phase Leader with learning walks |
| 2d) Opportunities for developing using and applying Maths within interventions to target specific children in KS1 and KS2 | HW SC | SENCO, Inclusion Leader, FC@N TAs (LC, SJ) | Training for First Class @ Number for KS1 and extending into lower KS2 (Autumn term) | % of children identified on the maths intervention will be making accelerated progress. | KS1 FC@N September 2016 Lower KS2 FC@N to be launched in Autumn term following training. |
| 3) Opportunities to develop Problem Solving & Reasoning within maths |  |  |  |  |  |
| 3a) Teachers and support staff use Problem Solving & Reasoning activities to help embed Using & Applying knowledge in maths | Sarah T / Paul | Teaching and support staff, subject leads, external CPD providers | Training resources Resources to be sourced and purchased via the staff development & training cost centre | Staff have a greater awareness of possible Problem Solving and Reasoning activities to use and what mastery within maths looks like – this is reflected in the learning opportunities evidenced in books | Autumn 2016 Reviewed termly within Phase Leader tasks set by SLT |
| 3b) Children’s learning is challenged and stretch is provided through depth | Sarah T / Paul | Class teachers and support staff, maths leads | Training resources Resources to be sourced and purchased via the staff development & training cost centre | Increase % of children making expected progress. | Autumn 2016 |

| 4) A consistent approach to planning and assessment in maths |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Action | Leadership | Support | Resources | Success Criteria | Completion Date |
| 4a) Planning is developed from an agreed set of NC objectives and a consistent approach is applied across the school | Maths Leaders Jen D (EYFS) Hayley (KS1) Paul (KS2) | Class teachers, support staff, SLT Mentors | Lancs LGFL Curriculum planning documents | All year groups will be planning from the same document (Lancashire Planning) Subject leads hold a termly overview of objectives covered by each year group | Consistent document in place from September 2016 |
| 4b) Consistent use of summative assessment materials supports teacher judgements | Jon | Class teachers, support staff | Summative assessment documents – Assertive Mentoring and Focus Education | Use of assessment papers support teacher judgement prior to pupil progress, accuracy of data is supported through use of formative and summative assessment | Consistent approach in place in place from October 2016 – See Assessment timetable. |
| 4c) Formative assessment is supported through the consistency in marking and response to marking, including challenge through questioning | Phase Leaders LT, JD, JB, CK | Marking working party, SLT Mentors, teachers and support staff | Marking policy distributed to staff | Clear marking policy in place Book scrutiny evidences a consistent approach with children responding appropriately to marking Pupil voice evidences the value of marking and the children’s understanding of its purpose | Monitoring of marking through termly book scrutiny. |
| 4d) Planning is informed by effective summative/formative assessments and Pre-Teach Friday tasks | Sarah T | SLT, Class teachers, support staff | Summative assessment documents – Assertive Mentoring and focus education Termly Overview grids to plug identified gaps | Use of summative assessment / Pre-Teach Friday tasks inform next steps in planning. Targeted groups are identified and monitored to make accelerated progress. | Consistent approach in place in place from September 2016 – Pre-Teach Friday Learning walks by SLT. |
| 4e) Calculation methods are linked to specific year group expectations within simplified calculation policy | Maths Leaders Jen D (EYFS) Hayley (KS1) Paul (KS2) | Class teachers, support staff, SLT Mentors | Revised Calculation Policy | Use of specific formal methods will be embedded across the school linked to ability stage. These will be displayed in each classroom. | Consistent approach in place for formal methods for Addition, Subtraction, Multiplication and Division by September 2016 |
| 5) Embedded opportunities to practise maths skills in ‘real-life’ contexts |  |  |  |  |  |
| 5a) Children are given ‘real-life’ opportunities to practice and embed skills | Maths Leaders Jen D (EYFS) Hayley (KS1) Paul (KS2) | Teachers and support staff | Teaching and learning resources Subject and class cost centres as appropriate | Opportunities such as baking, visits to shops, enterprise and topic related maths enable the children to work within real-life circumstances. Pupil and staff voice reflect the benefits of such learning. | Monitoring through pupil voice and evidence within termly book scrutiny. |

| Area of Responsibility: Monitoring Impact of Teaching and Learning |  |  |  | Links with agencies: SLE from MTSA Anthony Reddy – Reddy Made Consultancy QA - Deb Hunton Gavin Shortall (St. James Primary) |  |
| --- | --- | --- | --- | --- | --- |
| Objectives: 1) Progress towards 85% of children meeting year group expectations (core subjects) 2) Challenge evident for all children in all aspects of lessons, including Skillsburst activities at the start of the day 3) Developed provision for G&T children 4) Depth and mastery opportunities available across the curriculum 5) Key learning behaviours are embedded and consistent across the school |  |  |  |  |  |
| 1) Progress towards 85% of children meeting year group expectations (Core subjects) |  |  |  |  |  |
| Key Action | Leadership | Support | Resources | Success Criteria | Completion Date |
| 1a) A clear cycle of planning, teaching and assessment enables the children to make maximum progress | Phase Leaders LT, JD, JB, CK | SLT Mentors, Teachers, support staff | Planning and assessment resources, teaching and learning resources | Book scrutiny reflects the cycle of plan, teach and assess and it is clear that misconceptions are addressed and that pace and challenge are adequate | Reviewed termly within Phase Leader tasks set by SLT |
| 1b) Through effective planning and teaching, children are enabled to make progress towards expected outcomes | Phase Leaders LT, JD, JB, CK Jon and Sarah T | SLT, teachers and support staff | Learning resources Pupil progress documents | % of children at expected increases termly Progress towards expected outcomes is reflected through pupil progress | Reviewed termly within Pupil Progress |
| 1c) The pitch of lessons reflect the increasing demands of the national curriculum expectations. | Jon and Sarah T | SLT, teachers and support staff | Staff INSET time, lesson observations and feedback, peer observations, weekly year group meetings | % of children at expected increases termly Consistency and parity across year groups evident, pitch and expectations evidenced through books and lesson observations | Reviewed termly within Phase Leader tasks set by SLT, Learning Walks and QA Learning Review – 28/9/16 |
| 2. Challenge evident for all children in all aspects of lessons, including Skillsburst activities at the start of the day |  |  |  |  |  |
| 2a) Challenge is evident within the start of day Skillsburst activities | Phase Leaders LT, JD, JB, CK Jon and Sarah T | Teachers, support staff and SLT Mentors | Teaching and learning resources | Teachers maximise on ‘pockets of time’ to help embed learning expectations. | Reviewed termly within Phase Leader tasks set by SLT, Learning Walks and QA Learning Review – 28/9/16 |
| 2b) All learners are challenged in all aspects of the lessons | Helen W and Sam Inclusion Team | Teachers and support staff Inclusion Team | Teaching and learning resources | Teachers maximise on ‘pockets of time’ to help embed learning for all learners including G&T pupils | Inclusion Team Learning Walks and QA Learning Review – 28/9/16 |
| 2c) Marking is purposeful and enables the children to move their learning forward | Phase Leaders LT, JD, JB, CK | Teachers and support staff, SLT mentors and Ellie Russell (T&L Gov) | Marking policy Book scrutiny monitoring sheets | Books are marked in line with Marking policy All children respond appropriately to marking | Reviewed termly within Phase Leader tasks set by SLT |

| 3) Developed provision for SEND and G&T children |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Action | Leadership | Support | Resources | Success Criteria | Completion Date |
| 3a) Tracking of G&T children consistent with tracking of SEND children | Nicky/Helen Woolf, Sam | Teachers | Tracking documents | Consistent tracking system in place for G&T children | December 2016 – See Assessment Calendar. |
| 3b) Case studies reflect the opportunities available to SEND, G&T children and evaluate the impact on learning and progress | Nicky | Teachers and support staff | Case study format | Case studies completed termly for specified children Impact document completed termly by G&T lead, Inclusion Lead | Termly impact document completed by Phase Leaders and presented to SLT |
| 3c) Children have opportunities to share skills as appropriate, including peer tutoring | Nicky | Teachers and support staff | Teaching and learning opportunities | Pupil voice reflects opportunities available Children on G&T register sharing skills across school | Termly impact document completed by G&T lead - presented to SLT |
| 4) Depth and mastery opportunities available across the curriculum |  |  |  |  |  |
| 4a) Staff have a developed awareness of what depth and mastery is | Sarah T | Teachers and support staff | Staff INSET, CPD resources | Staff voice reflects that staff feel more confident in their understanding of depth and mastery | Spring Term 2017 |
| 4b) Staff have the opportunity to consider depth and mastery opportunities relevant to specific year group/s | Sarah T | Teachers and support staff | Staff INSET, curriculum objectives/outcomes | Opportunities for depth and mastery within the curriculum are planned for | Spring Term 2017 |
| 4c) Areas of best practice/confidence identified and shared | Jon and Sarah T | Teachers and support staff | Staff voice | Evidence of best practice established Increase in % of children at exceeding and mastery | Spring Term 2017 |
| 4c) Evidence of opportunities to work in depth or at mastery level | Sarah G (Reading) Kat (Writing) Paul (Maths) | Teachers and support staff | Planning, teaching and learning resources – Portfolio produced. | Increase in % of children at exceeding and mastery on a termly basis Evidenced through book scrutiny | Summer Term 2017 |
| 4e) Portfolio of depth/mastery challenges generated | Sarah G (Reading) Kat (Writing) Paul (Maths) | Teachers and support staff Ellie Russell | Portfolio, examples of work, samples of planning and learning activities | Complete portfolio – demonstrating evidence of depth and mastery per year group | Summer Term 2017 |

| 5) Key learning behaviours are embedded and consistent across the school |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Action | Leadership | Support | Resources | Success Criteria | Completion Date |
| 5a) Behaviour for learning continues to be embedded across school | Jon, Sarah T And Donna | Teachers and support staff, school council | School expectations, CPOMS behaviour reports, assembly time | Behaviour and safety judged as Outstanding in Autumn QA visit | To be reviewed termly |
| 5b) Independence for learning continues to be promoted | Phase Leaders LT, JD, JB, CK Inclusion Team | Teachers and support staff | Incredibly independent displays | Children make independent choices within their learning Independence is evident within all learners at an age appropriate level | Reviewed within QA T&L Review 28/9/16 Termly impact document completed by Phase Leaders and Inclusion Lead to be presented within SLT meeting |
| 5c) Children choose and access resources to support learning with increasing independence | Phase Leaders LT, JD, JB, CK Inclusion Team | Teachers and support staff, children | Teaching and learning resources from class budgets | Resources support and enhance learning, enabling children to make at least expected progress (data reflects this) |  |
| 5d) Opportunities to work in mixed-ability groups are utilized where appropriate | Phase Leaders LT, JD, JB, CK Inclusion Team | Teachers and support staff | Groupings of children | Flexible groupings support all children in making expected progress (data reflects this) |  |
| 5e) Opportunities for children to access more structured focused activities during lunch and playtimes | Donna | Kieran Nicky Midge SLOs Fit for Learning and Pastoral Team | PE playtime resources Art / Music club resources, LO CPD | Behaviour and safety judged as Outstanding in Autumn QA visit | Timetabled activities set up by October 2016 To be reviewed termly by SLT and SLOs |

| Area of Responsibility: Application of Comprehension skills in Reading |  |  |  | Links with agencies: Barlow Hall Primary Rising Stars Brilliant Publications – Reading Comprehension books Inference training (Barlow Hall) |  |
| --- | --- | --- | --- | --- | --- |
| Objectives: 1) Progress towards 85% of children meeting year group expectations 2) Embedded opportunities to apply reading comprehension skills throughout the school day 3) A consistent approach to planning and assessment in Reading |  |  |  |  |  |
| 1) Progress towards 85% of children meeting year group expectations |  |  |  |  |  |
| Key Action | Leadership | Support | Resources | Success Criteria | Completion Date |
| 1a. Each year group (Y1-Y6) completes weekly reading comprehension activities to develop comprehension skills | Sarah G English Team Phase Leaders LT, JD, JB, CK | Reading lead (Sarah G), class teachers and support staff | Brilliant Publications – Reading Comprehension books | Children will develop more stamina and confidence to complete sustained written comprehensions | October 2016 |
| 1b. Cycle of formative and summative assessments inform planning, enabling gaps to be plugged | Sarah G English Team Phase Leaders LT, JD, JB, CK | Reading lead (Sarah G), class teachers and support staff | Summative assessment materials | Formative and summative assessments used to plug gaps – increase in % of children meeting ‘expected’ throughout the year | Reading assessments to be carried out half termly |
| 1c. Rigour in Guided Reading planning enables the children to make maximum progress | Sarah G English Team Phase Leaders LT, JD, JB, CK | Reading lead (Sarah G), class teachers and support staff | Guided Reading Ppanning files and resources | % of children making expected+ progress Guided Reading Planning files within each class. Comprehension and Guided Reading resources are shared and developed by teaching and support staff | Guided Reading planning to be set up September 2016. Guided Reading resources to be placed in shared area – to build up resources (Reviewed half termly by Reading Lead) |
| 2) Embedded opportunities to apply reading comprehension skills throughout the week |  |  |  |  |  |
| 2a) Reading comprehension skills continues to be taught weekly in subjects across the curriculum | Sarah G English Team Phase Leaders LT, JD, JB, CK | Reading lead (Sarah G), class teachers and support staff | Reading comprehension resources, Phase Leadership time for Guided reading evidence trails | Termly book Guided Reading scrutiny shows consistent opportunities for using and applying reading comprehension skills in topic, termly pupil voice reflects opportunities available | Reviewed termly within Reading Lead and Phase Leader tasks set by SLT |
| 3) A consistent approach to planning and assessment in Reading |  |  |  |  |  |
| 3a) Guided Reading planning is developed from an agreed set of NC objectives and a consistent approach is applied across the school | Sarah G English Team | Reading lead (Sarah G), class teachers and support staff | National Curriculum planning documents | All year groups will be planning from the same document and using a consistent planning file format. | Guided Reading planning files to be set up September 2016. |

| 3b) Consistent use of summative assessment materials supports teacher judgements | Jon | Class teachers, support staff | Summative assessment documents – Rising Stars | Use of assessment papers support teacher judgement prior to pupil progress, accuracy of data is supported through use of formative and summative assessment | Consistent approach in place in place from October 2016 – See Assessment timetable. |
| --- | --- | --- | --- | --- | --- |
| 3c) Planning is informed by effective summative/formative assessments and Pre -Teach Friday tasks | Sarah T Sarah G | Reading lead (Sarah G), Class teachers, support staff | Summative assessment documents – Brilliant Comprehension tasks Termly Overview grids to plug identified gaps | Use of summative assessment / Pre-Teach Friday tasks inform next steps in Guided Reading planning. Targeted groups are identified and monitored to make accelerated progress. | Consistent approach in place in place from September 2016 – Pre-Teach Friday Learning walks by SLT. |